## SAELAR
🛡️ SAELAR — User Acceptance Test Plan
Security Architecture & Evaluation ¦ NIST 800-53 Rev 5 ¦ Cloud Assessment Platform
Test ID | No Source Req'd | Category | Metric | Test Scenario | Acceptance Criteria | Steps to Execute | Expected Result | Pass/Fail | Notes | Tester | Date
SAE-SEC-01 | ✓ | Security | Data Protection | AWS credentials are stored securely and not exposed in UI or logs | Credentials are never displayed in plain text; secret key masked; no credential leakage in browser console or logs | 1. Configure AWS credentials in SAELAR; 2. Inspect page source and browser console; 3. Check that only masked/placeholder values visible | No credential exposure in any client-side context
SAE-SEC-02 | ✓ | Security | Session Handling | Application enforces secure session behavior | Session does not persist sensitive data in URL parameters; logout clears credentials from session | 1. Log in with credentials; 2. Check URL for any credential strings; 3. Log out and verify session cleared | No credentials in URL; clean logout
SAE-SEC-03 | ✓ | Security | Communication | Application supports HTTPS when configured | When SSL certs present | app serves over HTTPS; no mixed content warnings | 1. Configure SSL; 2. Access via https://; 3. Verify padlock and no mixed-content errors | HTTPS available; no security warnings
SAE-SEC-04 | ✓ | Security | Air-Gapped Mode | Air-gapped mode operates without external network | When SAELAR_AIRGAPPED=true and Ollama running | all features work with no outbound AWS/internet calls | 1. Set SAELAR_AIRGAPPED=true; 2. Disconnect or block outbound; 3. Run assessment and AI features | Full functionality without network
SAE-REL-01 | ✓ | Relevance | NIST Coverage | NIST 800-53 Rev 5 controls are accurately represented | All 13 cloud-relevant control families assessed; control IDs and descriptions align with NIST Rev 5 | 1. Run NIST Assessment; 2. Review control list; 3. Cross-reference sample controls to NIST 800-53 Rev 5 | Control alignment verified
SAE-REL-02 | ✓ | Relevance | AWS Service Coverage | Assessment queries correct AWS services | Findings reference actual AWS resources; IAM/S3/EC2/CloudTrail/Config etc. queried appropriately | 1. Run cloud assessment; 2. Verify findings map to real AWS API responses; 3. Spot-check IAM/EC2/S3 findings | Accurate AWS-based findings
SAE-REL-03 | ✓ | Relevance | Security Hub Integration | Security Hub findings map to NIST controls | Security Hub findings imported and correctly mapped to NIST 800-53 control families | 1. Enable Security Hub; 2. Run assessment; 3. View Security Hub findings tab; 4. Verify NIST mapping | Findings properly mapped
SAE-REL-04 | ✓ | Relevance | Risk Scoring | Risk scores follow NIST SP 800-30 methodology | Risk matrix (Likelihood x Impact) produces severity levels; CRITICAL/HIGH/MEDIUM/LOW thresholds correct | 1. Run assessment with mix of findings; 2. Review risk scores; 3. Verify escalation rules (e.g. 2+ CRITICAL = Overall CRITICAL) | Risk scoring matches methodology
SAE-REL-05 | ✓ | Relevance | BOD 22-01 | CISA KEV findings are identified | BOD 22-01 tab shows KEV-listed vulnerabilities when present; remediation timeline guidance provided | 1. Import or simulate KEV findings; 2. Check BOD 22-01 tab; 3. Verify KEV identification | KEV items correctly flagged
SAE-USE-01 | ✓ | Ease of Use | Navigation | User can navigate between all major tabs within 3 clicks | NIST Assessment/AWS Console/Chad/Risk Calculator/SSP Generator/BOD 22-01/Threat Modeling/Artifacts accessible | 1. Start from home; 2. Navigate to each tab; 3. Count clicks required | All tabs reachable in ≤3 clicks
SAE-USE-02 | ✓ | Ease of Use | Credential Setup | AWS credential configuration is intuitive | Credential screen has clear fields; validation provides actionable error messages; successful config shows confirmation | 1. Open credential config; 2. Enter invalid then valid creds; 3. Verify validation feedback | Clear UX; helpful error messages
SAE-USE-03 | ✓ | Ease of Use | Dashboard Readability | Dashboard metrics and charts are legible and meaningful | Metrics show pass/fail counts; charts render correctly; color coding is consistent | 1. Run assessment; 2. View dashboard; 3. Check charts and metrics | Readable and meaningful summary
SAE-USE-04 | ✓ | Ease of Use | Document Generation | SSP and POA&M generation requires minimal user input | User selects options and clicks Generate; document downloads without excessive form filling | 1. Run assessment; 2. Open SSP Generator; 3. Generate SSP and POA&M with minimal input | Documents generated successfully
SAE-USE-05 | ✓ | Ease of Use | Export Options | Results exportable in usable formats | CSV/Excel/PDF exports available where applicable; exported data is complete and structured | 1. Generate assessment; 2. Export in each format; 3. Open and verify content | Exports complete and usable
SAE-FUN-01 | ✓ | Functionality | Cloud Assessment | NIST cloud assessment runs to completion | Full assessment completes without fatal errors; results displayed; all control families processed | 1. Configure valid AWS credentials; 2. Run NIST Assessment; 3. Wait for completion | Assessment completes successfully
SAE-FUN-02 | ✓ | Functionality | AI Chad | Chad AI assistant responds to security questions | Chad provides relevant answers; can generate charts and remediation guidance; graceful fallback if Bedrock unavailable | 1. Open Chad tab; 2. Ask security question; 3. Request chart or remediation | Relevant AI response or fallback
SAE-FUN-03 | ✓ | Functionality | S3 Document Upload | Documents can be uploaded to S3 when configured | S3 bucket selectable; upload succeeds; documents listable and downloadable | 1. Configure S3 bucket; 2. Upload SSP/POA&M; 3. List and download | S3 integration works
SAE-FUN-04 | ✓ | Functionality | Threat Modeling | Threat modeling module displays control-to-threat mapping | MITRE ATT&CK mapping visible; asset-threat relationships shown; exportable | 1. Run assessment; 2. Open Threat Modeling; 3. Review mappings | Threat modeling functional
SAE-FUN-05 | ✓ | Functionality | Artifacts Management | Artifacts/evidence can be managed | Upload download and organize assessment artifacts | 1. Open Artifacts tab; 2. Upload file; 3. List and download | Artifact management works
SAE-PERF-01 | ✓ | Performance | Assessment Speed | Cloud assessment completes within reasonable time | Full NIST assessment completes in under 10 minutes for typical account | 1. Run full assessment; 2. Record start and end time | Completes in <10 min (or documented SLA)
SAE-PERF-02 | ✓ | Performance | Page Load | Initial page load responsive | Application loads within 15 seconds on standard connection | 1. Clear cache; 2. Load app; 3. Measure time to interactive | Load time acceptable
SAE-COMP-01 | ✓ | Compliance | Audit Trail | Assessment history and actions are traceable | Assessment runs and key actions produce auditable records where applicable | 1. Run assessment; 2. Review any logs or history; 3. Verify traceability | Audit trail present
SAE-COMP-02 | ✓ | Compliance | FedRAMP Alignment | Output aligns with FedRAMP documentation expectations | SSP and POA&M structure suitable for FedRAMP packages | 1. Generate SSP and POA&M; 2. Review against FedRAMP template expectations | Output FedRAMP-suitable
📋 LEGEND & INSTRUCTIONS
• Pass/Fail: Select from dropdown (Pass, Fail, N/A, Blocked)
• Category colors (left border): Security=Red ¦ Relevance=Green ¦ Ease of Use=Violet ¦ Functionality=Blue ¦ Performance=Amber ¦ Compliance=Teal
• Use header filter arrows to sort/filter by Category, Pass/Fail, or any column
• Freeze panes: Row 3 (headers) stay visible when scrolling
• No Source Req'd (✓): All tests are black-box — run via UI, network inspection (browser DevTools), or CLI. No application source code access needed.

## SOPRA
🛡️ SOPRA — User Acceptance Test Plan
SAE On-Premise Risk Assessment ¦ 200 Controls ¦ ISSO Toolkit ¦ AI-Powered Automation
Test ID | No Source Req'd | Category | Metric | Test Scenario | Acceptance Criteria | Steps to Execute | Expected Result | Pass/Fail | Notes | Tester | Date
SOP-SEC-01 | ✓ | Security | Data Protection | Assessment data and credentials handled securely | No PII or raw evidence sent to AI; AWS credentials not exposed in UI; file-based storage has appropriate permissions | 1. Run assessment; 2. Use AI features; 3. Inspect network requests for data leakage; 4. Check file permissions | No credential or PII exposure
SOP-SEC-02 | ✓ | Security | Session Handling | Session state and persistence secure | Cross-tab data sharing via .sopra_results.json does not expose secrets; Back to Dashboard works without leaking state | 1. Open multiple tabs (assessment/remediation/ISSO); 2. Verify data sharing; 3. Check for sensitive data in URLs | Secure state handling
SOP-SEC-03 | ✓ | Security | AI Transparency | AI-generated content clearly labeled | All AI output tagged with visible badge; human can distinguish AI vs manual content | 1. Use POA&M AI generate; 2. Use Risk Acceptance AI draft; 3. Use evidence analysis; 4. Verify badges present | AI content clearly labeled
SOP-SEC-04 | ✓ | Security | Fallback Behavior | Application functions without AI when Bedrock unavailable | Graceful fallback to templates; no crashes; user informed when AI unavailable | 1. Disable Bedrock or use invalid creds; 2. Trigger each AI feature; 3. Verify template fallback | No crash; fallback works
SOP-REL-01 | ✓ | Relevance | NIST/CIS Alignment | 200 controls align to NIST 800-53 Rev 5 and CIS v8 | Control definitions and mappings accurate; bidirectional crosswalk correct | 1. Open Control Crosswalk; 2. Review NIST and CIS mappings; 3. Spot-check against framework docs | Accurate control alignment
SOP-REL-02 | ✓ | Relevance | FIPS 199 Baselines | FIPS 199 baselines filter controls correctly | Low (75) Moderate (155) High (200) baselines applied; filtering changes control set as expected | 1. Select Low baseline; 2. Count controls; 3. Switch to Moderate and High; 4. Verify counts | Baseline filtering correct
SOP-REL-03 | ✓ | Relevance | ISSO Workflow Relevance | ISSO Toolkit tools match real ATO workflows | POA&M Risk Acceptance Evidence Inheritance Scheduling Approvals STIG Import Incident Correlation align with ISSO tasks | 1. Open each ISSO tool; 2. Verify workflow fit; 3. Confirm output format matches ATO needs | Tools match ISSO workflows
SOP-REL-04 | ✓ | Relevance | Vulnerability Management | Automated Vulnerability Management provides actionable remediation | Attack chains remediation plans validation scripts impact analysis and ticket generation produce useful output | 1. Run assessment with failures; 2. Open Vulnerability Management; 3. Use each sub-tool | Actionable remediation output
SOP-REL-05 | ✓ | Relevance | SSP Generation | SSP narratives use formal RMF language | Generated SSP control narratives are auditor-ready and use appropriate terminology | 1. Run assessment; 2. Generate SSP with AI narratives; 3. Review sample narratives | RMF-appropriate language
SOP-USE-01 | ✓ | Ease of Use | Navigation | User can navigate between all main pages within 3 clicks | Dashboard Assessment Reports Vulnerability Management SSP Generator AI Assistant Settings and ISSO Toolkit accessible | 1. Start from Dashboard; 2. Navigate to each page; 3. Count clicks | All pages reachable in ≤3 clicks
SOP-USE-02 | ✓ | Ease of Use | ISSO Toolkit Access | ISSO Toolkit opens in clear hub layout | Toolkit hub displays; 12 tools visible; navigation between tools intuitive | 1. Click ISSO Toolkit; 2. Review hub; 3. Navigate to 3 different tools | Clear hub layout; easy tool access
SOP-USE-03 | ✓ | Ease of Use | Assessment Workflow | Assessment import and manual entry straightforward | CSV import works; demo data loads; manual assessment UI clear | 1. Import CSV; 2. Load demo data; 3. Manually assess a few controls | Assessment workflow intuitive
SOP-USE-04 | ✓ | Ease of Use | AI Button Clarity | AI features triggered with single clear action | Each AI feature has obvious button; one click invokes; loading state shown | 1. Open POA&M; 2. Click AI Generate; 3. Repeat for Risk Acceptance Evidence etc | Single-click AI invocation
SOP-USE-05 | ✓ | Ease of Use | Reports and Export | Reports and exports usable | Reports page generates; exports (CSV/JSON) complete; format suitable for downstream use | 1. Run assessment; 2. Open Reports; 3. Export in available formats | Exports complete and usable
SOP-FUN-01 | ✓ | Functionality | Assessment | Full 200-control assessment runs to completion | Assessment completes; results persist; findings display correctly by category | 1. Run full assessment (CSV or demo); 2. Verify completion; 3. Check Dashboard and Reports | Assessment completes successfully
SOP-FUN-02 | ✓ | Functionality | AI POA&M Generation | AI generates POA&M entries for failed findings | One click produces POA&M entries with milestones due dates and responsible parties | 1. Run assessment with failures; 2. Open POA&M Tracker; 3. Click AI Generate POA&M | POA&M entries generated
SOP-FUN-03 | ✓ | Functionality | AI Risk Acceptance | AI drafts risk acceptance justification | AI produces operational justification compensating controls and residual risk assessment | 1. Open Risk Acceptance; 2. Select finding; 3. Click AI Draft Justification | Justification generated
SOP-FUN-04 | ✓ | Functionality | AI Evidence Analysis | AI analyzes evidence sufficiency | Per-artifact analysis returns Sufficient/Partial/Insufficient with recommendations | 1. Upload evidence; 2. Run Analyze Sufficiency; 3. Review output | Evidence analysis works
SOP-FUN-05 | ✓ | Functionality | AI Control Inheritance | AI classifies control inheritance | One click classifies controls as Inherited/Common/System-Specific with rationale | 1. Open Control Inheritance; 2. Click AI Classify All; 3. Review classifications | Inheritance classified
SOP-FUN-06 | ✓ | Functionality | AI STIG Mapping | AI maps STIG findings to SOPRA controls | Imported STIG results map to controls with confidence scores | 1. Import STIG/CIS results; 2. Run AI Map; 3. Verify mappings | STIG mapping works
SOP-FUN-07 | ✓ | Functionality | AI Incident Correlation | AI suggests related controls for incidents | Incident description yields control correlations with relevance scores | 1. Log incident; 2. Run AI Suggest Related; 3. Review suggestions | Correlation suggestions provided
SOP-FUN-08 | ✓ | Functionality | Continuous Monitoring | ConMon dashboard displays assessment timeline and advisories | ConMon shows threat level timeline and category advisories | 1. Open Continuous Monitoring; 2. Run assessment; 3. View ConMon | ConMon displays correctly
SOP-PERF-01 | ✓ | Performance | Assessment Speed | 200-control assessment completes in reasonable time | Assessment completes in under 5 minutes for demo/import scenarios | 1. Run assessment; 2. Record completion time | Completes in <5 min (or documented SLA)
SOP-PERF-02 | ✓ | Performance | AI Response Time | AI features respond within acceptable time | AI generation completes within 60 seconds per operation | 1. Trigger AI POA&M generate; 2. Trigger AI Risk draft; 3. Measure response time | AI response acceptable
SOP-PERF-03 | ✓ | Performance | Page Load | Navigation and page loads responsive | Page transitions under 5 seconds; no prolonged blank screens | 1. Navigate between 5 pages; 2. Note load times | Responsive navigation
SOP-COMP-01 | ✓ | Compliance | Audit Readiness | Output suitable for ATO package | POA&M Risk Acceptance SSP and Approval workflows produce audit-ready artifacts | 1. Generate POA&M Risk Acceptance SSP; 2. Review against ATO checklist | Output audit-ready
SOP-COMP-02 | ✓ | Compliance | Data Residency | AI sends only aggregate data no PII or raw evidence | Verifiable that only assessment metadata sent to Bedrock; no evidence uploads to cloud | 1. Use browser DevTools Network tab to inspect outbound requests during AI operations; 2. Confirm only aggregate metadata sent to Bedrock (no raw evidence or PII) | Data minimization verified
📋 LEGEND & INSTRUCTIONS
• Pass/Fail: Select from dropdown (Pass, Fail, N/A, Blocked)
• Category colors (left border): Security=Red ¦ Relevance=Green ¦ Ease of Use=Violet ¦ Functionality=Blue ¦ Performance=Amber ¦ Compliance=Teal
• Use header filter arrows to sort/filter by Category, Pass/Fail, or any column
• Freeze panes: Row 3 (headers) stay visible when scrolling
• No Source Req'd (✓): All tests are black-box — run via UI, network inspection (browser DevTools), or CLI. No application source code access needed.