## SOPRA UAT
🛡️ SOPRA — User Acceptance Test Plan
SAE On-Premise Risk Assessment ¦ 200 Controls ¦ ISSO Toolkit ¦ AI-Powered Automation
Test ID | Category | Metric | Test Scenario | Acceptance Criteria | Steps to Execute | Expected Result | Pass/Fail | Notes | Tester | Date
SOP-SEC-01 | Security | Data Protection | Assessment data and credentials handled securely | No PII or raw evidence sent to AI; AWS credentials not exposed in UI; file-based storage has appropriate permissions | 1. Run assessment; 2. Use AI features; 3. Inspect network requests for data leakage; 4. Check file permissions | No credential or PII exposure
SOP-SEC-02 | Security | Session Handling | Session state and persistence secure | Cross-tab data sharing via .sopra_results.json does not expose secrets; Back to Dashboard works without leaking state | 1. Open multiple tabs (assessment/remediation/ISSO); 2. Verify data sharing; 3. Check for sensitive data in URLs | Secure state handling
SOP-SEC-03 | Security | AI Transparency | AI-generated content clearly labeled | All AI output tagged with visible badge; human can distinguish AI vs manual content | 1. Use POA&M AI generate; 2. Use Risk Acceptance AI draft; 3. Use evidence analysis; 4. Verify badges present | AI content clearly labeled
SOP-SEC-04 | Security | Fallback Behavior | Application functions without AI when Bedrock unavailable | Graceful fallback to templates; no crashes; user informed when AI unavailable | 1. Disable Bedrock or use invalid creds; 2. Trigger each AI feature; 3. Verify template fallback | No crash; fallback works
SOP-REL-01 | Relevance | NIST/CIS Alignment | 200 controls align to NIST 800-53 Rev 5 and CIS v8 | Control definitions and mappings accurate; bidirectional crosswalk correct | 1. Open Control Crosswalk; 2. Review NIST and CIS mappings; 3. Spot-check against framework docs | Accurate control alignment
SOP-REL-02 | Relevance | FIPS 199 Baselines | FIPS 199 baselines filter controls correctly | Low (75) Moderate (155) High (200) baselines applied; filtering changes control set as expected | 1. Select Low baseline; 2. Count controls; 3. Switch to Moderate and High; 4. Verify counts | Baseline filtering correct
SOP-REL-03 | Relevance | ISSO Workflow Relevance | ISSO Toolkit tools match real ATO workflows | POA&M Risk Acceptance Evidence Inheritance Scheduling Approvals STIG Import Incident Correlation align with ISSO tasks | 1. Open each ISSO tool; 2. Verify workflow fit; 3. Confirm output format matches ATO needs | Tools match ISSO workflows
SOP-REL-04 | Relevance | Vulnerability Management | Automated Vulnerability Management provides actionable remediation | Attack chains remediation plans validation scripts impact analysis and ticket generation produce useful output | 1. Run assessment with failures; 2. Open Vulnerability Management; 3. Use each sub-tool | Actionable remediation output
SOP-REL-05 | Relevance | SSP Generation | SSP narratives use formal RMF language | Generated SSP control narratives are auditor-ready and use appropriate terminology | 1. Run assessment; 2. Generate SSP with AI narratives; 3. Review sample narratives | RMF-appropriate language
SOP-USE-01 | Ease of Use | Navigation | User can navigate between all main pages within 3 clicks | Dashboard Assessment Reports Vulnerability Management SSP Generator AI Assistant Settings and ISSO Toolkit accessible | 1. Start from Dashboard; 2. Navigate to each page; 3. Count clicks | All pages reachable in ≤3 clicks
SOP-USE-02 | Ease of Use | ISSO Toolkit Access | ISSO Toolkit opens in clear hub layout | Toolkit hub displays; 12 tools visible; navigation between tools intuitive | 1. Click ISSO Toolkit; 2. Review hub; 3. Navigate to 3 different tools | Clear hub layout; easy tool access
SOP-USE-03 | Ease of Use | Assessment Workflow | Assessment import and manual entry straightforward | CSV import works; demo data loads; manual assessment UI clear | 1. Import CSV; 2. Load demo data; 3. Manually assess a few controls | Assessment workflow intuitive
SOP-USE-04 | Ease of Use | AI Button Clarity | AI features triggered with single clear action | Each AI feature has obvious button; one click invokes; loading state shown | 1. Open POA&M; 2. Click AI Generate; 3. Repeat for Risk Acceptance Evidence etc | Single-click AI invocation
SOP-USE-05 | Ease of Use | Reports and Export | Reports and exports usable | Reports page generates; exports (CSV/JSON) complete; format suitable for downstream use | 1. Run assessment; 2. Open Reports; 3. Export in available formats | Exports complete and usable
SOP-FUN-01 | Functionality | Assessment | Full 200-control assessment runs to completion | Assessment completes; results persist; findings display correctly by category | 1. Run full assessment (CSV or demo); 2. Verify completion; 3. Check Dashboard and Reports | Assessment completes successfully
SOP-FUN-02 | Functionality | AI POA&M Generation | AI generates POA&M entries for failed findings | One click produces POA&M entries with milestones due dates and responsible parties | 1. Run assessment with failures; 2. Open POA&M Tracker; 3. Click AI Generate POA&M | POA&M entries generated
SOP-FUN-03 | Functionality | AI Risk Acceptance | AI drafts risk acceptance justification | AI produces operational justification compensating controls and residual risk assessment | 1. Open Risk Acceptance; 2. Select finding; 3. Click AI Draft Justification | Justification generated
SOP-FUN-04 | Functionality | AI Evidence Analysis | AI analyzes evidence sufficiency | Per-artifact analysis returns Sufficient/Partial/Insufficient with recommendations | 1. Upload evidence; 2. Run Analyze Sufficiency; 3. Review output | Evidence analysis works
SOP-FUN-05 | Functionality | AI Control Inheritance | AI classifies control inheritance | One click classifies controls as Inherited/Common/System-Specific with rationale | 1. Open Control Inheritance; 2. Click AI Classify All; 3. Review classifications | Inheritance classified
SOP-FUN-06 | Functionality | AI STIG Mapping | AI maps STIG findings to SOPRA controls | Imported STIG results map to controls with confidence scores | 1. Import STIG/CIS results; 2. Run AI Map; 3. Verify mappings | STIG mapping works
SOP-FUN-07 | Functionality | AI Incident Correlation | AI suggests related controls for incidents | Incident description yields control correlations with relevance scores | 1. Log incident; 2. Run AI Suggest Related; 3. Review suggestions | Correlation suggestions provided
SOP-FUN-08 | Functionality | Continuous Monitoring | ConMon dashboard displays assessment timeline and advisories | ConMon shows threat level timeline and category advisories | 1. Open Continuous Monitoring; 2. Run assessment; 3. View ConMon | ConMon displays correctly
SOP-PERF-01 | Performance | Assessment Speed | 200-control assessment completes in reasonable time | Assessment completes in under 5 minutes for demo/import scenarios | 1. Run assessment; 2. Record completion time | Completes in <5 min (or documented SLA)
SOP-PERF-02 | Performance | AI Response Time | AI features respond within acceptable time | AI generation completes within 60 seconds per operation | 1. Trigger AI POA&M generate; 2. Trigger AI Risk draft; 3. Measure response time | AI response acceptable
SOP-PERF-03 | Performance | Page Load | Navigation and page loads responsive | Page transitions under 5 seconds; no prolonged blank screens | 1. Navigate between 5 pages; 2. Note load times | Responsive navigation
SOP-COMP-01 | Compliance | Audit Readiness | Output suitable for ATO package | POA&M Risk Acceptance SSP and Approval workflows produce audit-ready artifacts | 1. Generate POA&M Risk Acceptance SSP; 2. Review against ATO checklist | Output audit-ready
SOP-COMP-02 | Compliance | Data Residency | AI sends only aggregate data no PII or raw evidence | Verifiable that only assessment metadata sent to Bedrock; no evidence uploads to cloud | 1. Review AI prompts/code or network; 2. Confirm data minimization | Data minimization verified
📋 LEGEND & INSTRUCTIONS
• Pass/Fail: Select from dropdown (Pass, Fail, N/A, Blocked)
• Category colors (left border): Security=Red ¦ Relevance=Green ¦ Ease of Use=Violet ¦ Functionality=Blue ¦ Performance=Amber ¦ Compliance=Teal
• Use header filter arrows to sort/filter by Category, Pass/Fail, or any column
• Freeze panes: Row 3 (headers) stay visible when scrolling